## Infomation
SWP391 - Group 1
I. Members |  |  |  | II. Project's information
# | Full name | Student ID | Total LOC | # | Field | Value
1 | Lê Minh Vương | QE170148 | 5470 | 1 | Project Name | Sale Dock
2 | Nguyễn Thị Thúy | QE170033 | 1710 | 2 | Repository | GitHub
3 | Đinh Quốc Chương | QE170097 | 2910 | 3 | SRS Document | SWP391 - Software Requirements Specification
4 | Hồ Trọng Nghĩa | QE170173 | 2680 | 4 | SDS Document | SWP391 - Software Design Specification
5 | Lâm Mỹ Linh | QE170023 | 1550 | 5 | Issues Report | SWP391 - Issues Report
6 | Nguyễn Thái Sơn | QE170212 | 1780 | 6 | Final Release Document | SWP391 - Final Release

## Project
Project
# | Title | Description | Screen / Function | Feature | Iteration | GitHub Issue | Assignee | Status | Priority | LOC | SRS | SDS | Note
1 | Write all model classes | Write all model to store database from database |  |  | Iteration 1 | #41 | Lê Minh Vương | Done | 1 | 500
2 | Write all DAO classes | Write all DAO classes to access data from database |  |  | Iteration 1 | #42 | Lê Minh Vương | Done | 2 | 700
3 | Write code base | Write code base for project |  |  | Iteration 2 | #44 | Lê Minh Vương | Done | 1 | 800
4 | Implement Docker for repository | Write Dockerfile and docker-compose.yml |  |  | Iteration 2 | #47 | Lê Minh Vương | Done | 1 | 200
5 | Write nav, sidenav, footer jsp | Write common jsp for reuse |  |  | Iteration 2 | #66 | Đinh Quốc Chương | Done | 1 | 150
6 | Implement login & forgot password pages | Implement login & forgot password pages | Login | Others | Iteration 2 | #77 | Hồ Trọng Nghĩa | Done | 1 | 200
7 | Implment customer page | Implment customer table page | List all customers | Customer Management | Iteration 2 | #70 | Nguyễn Thái Sơn | Done | 1 | 250
8 | Implment customer detail page | Implment customer detail page | Customer detail | Customer Management | Iteration 2 | #72 | Nguyễn Thị Thúy | Done | 1 | 150
9 | Implment add customer page | Implment add customer page | Add a customer | Customer Management | Iteration 2 | #67 | Lâm Mỹ Linh | Done | 1 | 200
10 | Implment product page | Implment product page | List all products | Product Management | Iteration 2 | #71 | Nguyễn Thái Sơn | Done | 2 | 250
11 | Implment order page | Implment order page | List all orders | Order Management | Iteration 2 | #69 | Lâm Mỹ Linh | Done | 2 | 250
12 | Design UI | Design UI |  |  | Iteration 2 |  | Lê Minh Vương | Done | 1 | 350
14 | Implment order detail | Implment order detail | Order detail | Order Management | Iteration 2 | #73 | Nguyễn Thị Thúy | Done | 2 | 150
15 | Implment product detail | Implment product detail | Product detail | Product Management | Iteration 2 | #68 | Đinh Quốc Chương | Done | 2 | 200
16 | Write APIs for dashboard | Write APIs for dashboard | Dashboard | Others | Iteration 2 | #79 | Lê Minh Vương | Done | 1 | 200
17 | Implment dashboard with charts | Implment dashboard with charts | Dashboard | Others | Iteration 2 | #80 | Lê Minh Vương | Done | 2 | 800
18 | Implment add product page | Implment add product page | Add a product | Product Management | Iteration 3 | #97 | Đinh Quốc Chương | Done | 1 | 300
19 | Implment add order page | Implment add order page | Add a order | Order Management | Iteration 3 | #98 | Hồ Trọng Nghĩa | Done | 1 | 600
20 | Implment update customer page | Implment update customer page (name, address) | Edit a customer | Customer Management | Iteration 3 | #120 | Nguyễn Thị Thúy | Done | 1 | 250
21 | Implment update product page | Implment update product page (name, price, image, note) | Edit a product | Product Management | Iteration 3 | #121 | Nguyễn Thái Sơn | Done | 1 | 300
22 | Implment update order page | Implment update order page (status if status not 'DONE' or 'CANCELLED') | Edit a order | Order Management | Iteration 3 |  | Lâm Mỹ Linh | Done | 1 | 200
23 | Implment paging for product page | Implment paging for product page | List all products | Product Management | Iteration 3 | #128 | Đinh Quốc Chương | Done | 2 | 300
24 | Implment paging for customer page | Implment paging for customer page | List all customers | Customer Management | Iteration 3 | #131 | Nguyễn Thị Thúy | Done | 1
25 | Implment paging for order page | Implment paging for order page | List all orders | Order Management | Iteration 3 | #132 | Hồ Trọng Nghĩa | Done | 2 | 300
26 | Write SRS document | Complete table in UC-E-1-1, UC-E-1-2, UC-E-1-3, UC-E-1-4 |  | Others | Iteration 3 |  | Lâm Mỹ Linh | Done | 1
27 | Write SRS document | Complete table in UC-E-2-1, UC-E-2-2, UC-E-2-3, UC-E-2-4 |  | Others | Iteration 3 |  | Nguyễn Thái Sơn | Done | 1
28 | Write SRS document | Complete table in UC-E-3-1, UC-E-3-3, UC-E-3-4 |  | Others | Iteration 3 |  | Nguyễn Thái Sơn | Done | 1
29 | Write SRS document | Complete table in UC-E-4-1, UC-E-4-2, UC-E-4-3 |  | Others | Iteration 3 |  | Lâm Mỹ Linh | Done | 1
30 | Download data as EXCEL | Download customer, product as EXCEL file |  | Others | Iteration 3 | #134 | Lê Minh Vương | Done | 1 | 400
31 | Add status order in list order | Add status order in list order | List all orders | Order Management | Iteration 3 | #134 | Lê Minh Vương | Done | 1 | 400
32 | Update paging for order page | When change page number to letter or negative number, it will redirect to 404 error page instead of returning to page 1 | List all orders | Order Management | Iteration 3 | #165 | Hồ Trọng Nghĩa | Done | 1 | 200
33 | Auto generate customer ID | Auto generate customer ID |  |  | Iteration 3 | #177 | Hồ Trọng Nghĩa | Done | 2 | 200
34 | Use `disable` instead of `readonly` in update pages | Use `disable` instead of `readonly` in update pages |  |  | Iteration 3 | #182 | Lê Minh Vương | Done | 1 | 200
35 | Write SRS document | Complete table Business Rule & add BR to UC |  | Others | Iteration 3 | #198 | Lê Minh Vương | Done | 2 | 100
36 | Complete Final Release Document |  |  |  | Iteration 4 | #195 | Lê Minh Vương | Done | 1 | 500
37 | Publish project on production |  |  |  | Iteration 4 | #197 | Lê Minh Vương | Done | 2 | 300
38 | Record video |  |  |  | Iteration 4 |  | Hồ Trọng Nghĩa | Done | 3 | 500
39 | System Test Document | List of all Test Cases implemented in the SaleDock project |  |  | Iteration 4 |  | Đinh Quốc Chương | Done | 1 | 500
40 | Slide for UC-E-1-1, UC-E-1-2, UC-E-1-3 |  |  |  | Iteration 4 |  | Lâm Mỹ Linh | Done | 1 | 200
41 | Slide for UC-E-1-4, UC-E-2-1, UC-E-2-2 |  |  |  | Iteration 4 |  | Nguyễn Thái Sơn | Done | 1 | 200
42 | Slide for UC-E-2-3, UC-E-2-4, UC-E-3-1 |  |  |  | Iteration 4 |  | Nguyễn Thị Thúy | Done | 1 | 200
43 | Slide for UC-E-3-2, UC-E-3-3, UC-E-3-4 |  |  |  | Iteration 4 |  | Đinh Quốc Chương | Done | 2 | 200
44 | Slide for UC-E-4-1, UC-E-4-2, UC-E-4-3 |  |  |  | Iteration 4 |  | Hồ Trọng Nghĩa | Done | 1 | 200
45 | Slide for Document |  |  |  | Iteration 4 |  | Đinh Quốc Chương | Done | 3 | 300
46

## Iteration 1
Iteration 1 | [7 empty] | Duration | Begin | 2024-01-01
[9 empty] | End | 2024-01-21
# | Title | Description | Screen / Function | Feature | GitHub Issue | Assignee | Status | Priority | LOC | SRS | SDS | Note
1 | Upload SDS document to Google Docs | Upload SDS document to Google Docs |  |  | #7 | Lâm Mỹ Linh | Done | 1 | 100
2 | Upload Final Release document to Google Docs | Upload Final Release document to Google Docs |  |  | #1 | Đinh Quốc Chương | Done | 1 | 60
3 | Upload SRS document to Google Docs | Upload SRS document to Google Docs |  |  | #2 | Nguyễn Thị Thúy | Done | 1 | 60
4 | Setup project | Setup project |  |  | #8 | Nguyễn Thái Sơn | Done | 1 | 80
5 | Design Database | Design and create Database |  |  | #3 | Hồ Trọng Nghĩa | Done | 1 | 100
6 | Upload Issues Report to Google Sheets | Upload Issues Report to Google Sheets |  |  | #5 | Lê Minh Vương | Done | 1 | 60
7 | Setup Imgbot | Setup Imgbot |  |  | #11 | Lê Minh Vương | Done | 3 | 0
8 | Setup CI | Setup auto build & release CI |  |  | #13 | Lê Minh Vương | Done | 4 | 50
9 | Upload Project Tracking to Google Sheets | Upload Project Tracking to Google Sheets |  |  | #4 | Lê Minh Vương | Done | 2 | 60
10 | Database: update SDS document | Add database design information in SDS document |  |  | #15 | Hồ Trọng Nghĩa | Done | 1 | 50
11 | Some errors in database | Some errors in the database design process |  |  | #17 | Hồ Trọng Nghĩa | Done | 1 | 10
12 | Write SRS - Draw the ERD model I.3 | Draw the ERD model and add Entities description |  |  | #25 | Hồ Trọng Nghĩa | Done | 1 | 70
13 | Write SRS - II.1 - Login Screen | Write detail function trigger, description and layout of Login Screen for SRS Document |  |  | #30 | Hồ Trọng Nghĩa | Done | 2 | 50
14 | Write SRS - II.2 - Forgot Password Screen | Write detail function trigger, description and layout of Forgot Password Screen for SRS Document |  |  | #29 | Lâm Mỹ Linh | Done | 1 | 50
15 | Write SRS - II.3 - Dashboard Screen | Write detail function trigger, description and layout of Dashboard Screen for SRS Document |  |  | #27 | Nguyễn Thái Sơn | Done | 1 | 150
16 | Write SRS - II.4 - Customer Management Screen | Write detail function trigger, description and layout of Customer Management Screen for SRS Document |  |  | #26 | Đinh Quốc Chương | Done | 1 | 200
17 | Write SRS - II.5 - Product Management Screen | Write detail function trigger, description and layout of Product Management Screen for SRS Document |  |  | #24 | Nguyễn Thị Thúy | Done | 1 | 200
18 | Write SRS - II.6 - Order Management Screen | Write detail function trigger, description and layout of Order Management Screen for SRS Document |  |  | #28 | Nguyễn Thị Thúy | Done | 2 | 200
19 | Write base for SRS Document | Write base form for SRS Document |  |  | #23 | Lê Minh Vương | Done | 1 | 250
20 | Write SDS - 2 - Draw Sequence Diagram | Draw Sequence Diagram for all feature in system |  |  | #39 | Hồ Trọng Nghĩa | Done | 1 | 200
21 | Write SDS - 2.1 - Design UI for Login Screen | Draw Class Diagram, Sequence Diagram and then description detail Class Specification, Database Queries for Login |  |  | #33 | Đinh Quốc Chương | Done | 1 | 200
22 | Write SDS - 2.2 - Design UI for Forgot Password Screen | Draw Class Diagram, Sequence Diagram and then description detail Class Specification, Database Queries for Forgot Password |  |  | #34 | Hồ Trọng Nghĩa | Done | 2 | 200
23 | Write SDS - 2.3 - Design UI for Dashboard Screen | Draw Class Diagram, Sequence Diagram and then description detail Class Specification, Database Queries for Dashboard |  |  | #26 | Nguyễn Thái Sơn | Done | 1 | 200
24 | Write SDS - 2.4 - Design UI for Customer Management Screen | Draw Class Diagram, Sequence Diagram and then description detail Class Specification, Database Queries for Customer Management |  |  | #37 | Lâm Mỹ Linh | Done | 1 | 200
25 | Write SDS - 2.5 - Design UI for Product Management Screen | Draw Class Diagram, Sequence Diagram and then description detail Class Specification, Database Queries for Product Management |  |  | #38 | Nguyễn Thị Thúy | Done | 1 | 200
26 | Write SDS - 2.6 - Design UI for Order Management Screen | Draw Class Diagram, Sequence Diagram and then description detail Class Specification, Database Queries for Order Management |  |  | #35 | Đinh Quốc Chương | Done | 2 | 200
27 | Write all model classes | Write all model to store database from database |  |  | #41 | Lê Minh Vương | Done | 1 | 500
28 | Write all DAO classes | Write all DAO classes to access data from database |  |  | #42 | Lê Minh Vương | Done | 2 | 700

## Iteration 2
Iteration 2 | [7 empty] | Duration | Begin | 2024-01-22
[9 empty] | End | 2024-02-25
# | Title | Description | Screen / Function | Feature | GitHub Issue | Assignee | Status | Priority | LOC | SRS | SDS | Note
1 | Write code base | Write code base for project |  |  | #44 | Lê Minh Vương | Done | 1 | 800
2 | Implement Docker for repository | Write Dockerfile and docker-compose.yml |  |  | #47 | Lê Minh Vương | Done | 1 | 200
3 | Write nav, sidenav, footer jsp | Write common jsp for reuse |  |  | #66 | Đinh Quốc Chương | Done | 1 | 150
4 | Implement login & forgot password pages | Implement login & forgot password pages | Login | Others | #77 | Hồ Trọng Nghĩa | Done | 1 | 200
5 | Implment customer page | Implment customer table page | List all customers | Customer Management | #70 | Nguyễn Thái Sơn | Done | 1 | 250
6 | Implment customer detail page | Implment customer detail page | Customer detail | Customer Management | #72 | Nguyễn Thị Thúy | Done | 1 | 150
7 | Implment add customer page | Implment add customer page | Add a customer | Customer Management | #67 | Lâm Mỹ Linh | Done | 1 | 200
8 | Implment product page | Implment product page | List all products | Product Management | #71 | Nguyễn Thái Sơn | Done | 2 | 250
9 | Implment order page | Implment order page | List all orders | Order Management | #69 | Lâm Mỹ Linh | Done | 2 | 250
10 | Design UI | Design UI |  |  | #65 | Lê Minh Vương | Done | 1 | 350
12 | Implment order detail | Implment order detail | Order detail | Order Management | #73 | Nguyễn Thị Thúy | Done | 2 | 150
13 | Implment product detail | Implment product detail | Product detail | Product Management | #68 | Đinh Quốc Chương | Done | 2 | 200
14 | Write APIs for dashboard | Write APIs for dashboard | Dashboard | Others | #79 | Lê Minh Vương | Done | 1 | 200
15 | Implment dashboard with charts | Implment dashboard with charts | Dashboard | Others | #80 | Lê Minh Vương | Done | 2 | 800

## Iteration 3
Iteration 3 | [7 empty] | Duration | Begin | 2024-02-26
[9 empty] | End | 2024-03-17
# | Title | Description | Screen / Function | Feature | GitHub Issue | Assignee | Status | Priority | LOC | SRS | SDS | Note
1 | Implment add product page | Implment add product page | Add a product | Product Management | #97 | Đinh Quốc Chương | Done | 1 | 300
2 | Implment add order page | Implment add order page | Add a order | Order Management | #123 | Hồ Trọng Nghĩa | Done | 1 | 600
3 | Implment update customer page | Implment update customer page (name, address) | Edit a customer | Customer Management | #120 | Nguyễn Thị Thúy | Done | 1 | 250
4 | Implment update product page | Implment update product page (name, price, image, note) | Edit a product | Product Management | #121 | Nguyễn Thái Sơn | Done | 1 | 300
5 | Implment update order page | Implment update order page (status if status not 'DONE' or 'CANCELLED') | Edit a order | Order Management | #122 | Lâm Mỹ Linh | Done | 1 | 200
6 | Implment paging for product page | Implment paging for product page | List all products | Product Management | #128 | Đinh Quốc Chương | Done | 2 | 300
7 | Implment paging for customer page | Implment paging for customer page | List all customers | Customer Management | #131 | Nguyễn Thị Thúy | Done | 2 | 300
8 | Implment paging for order page | Implment paging for order page | List all orders | Order Management | #132 | Hồ Trọng Nghĩa | Done | 2 | 300
9 | Write SRS document | Complete table in UC-E-1-1, UC-E-1-2, UC-E-1-3, UC-E-1-4 |  | Others |  | Lâm Mỹ Linh | Done | 4 | 200
10 | Write SRS document | Complete table in UC-E-2-1, UC-E-2-2, UC-E-2-3, UC-E-2-4 |  | Others |  | Nguyễn Thái Sơn | Done | 3 | 200
11 | Write SRS document | Complete table in UC-E-3-1, UC-E-3-3, UC-E-3-4 |  | Others |  | Nguyễn Thái Sơn | Done | 5 | 150
12 | Write SRS document | Complete table in UC-E-4-1, UC-E-4-2, UC-E-4-3 |  | Others |  | Lâm Mỹ Linh | Done | 5 | 150
13 | Download data as EXCEL | Download customer, product as EXCEL file |  | Others | #134 | Lê Minh Vương | Done | 1 | 400
14 | Add status order in list order | Add status order in list order | List all orders | Order Management | #165 | Hồ Trọng Nghĩa | Done | 1 | 200
15 | Update paging for order page | When change page number to letter or negative number, it will redirect to 404 error page instead of returning to page 1 | List all orders | Order Management | #177 | Hồ Trọng Nghĩa | Done | 2 | 200
16 | Auto generate customer ID | Auto generate customer ID |  |  | #182 | Lê Minh Vương | Done | 1 | 200
17 | Use `disable` instead of `readonly` in update pages | Use `disable` instead of `readonly` in update pages |  |  | #198 | Lê Minh Vương | Done | 2 | 100
18 | Write SRS document | Complete table Business Rule & add BR to UC |  | Others |  | Đinh Quốc Chương | Done | 1 | 300

## Iteration 4
Iteration 4 | [7 empty] | Duration | Begin | 2024-03-18
[9 empty] | End | 2024-03-24
# | Title | Description | Screen / Function | Feature | GitHub Issue | Assignee | Status | Priority | LOC | SRS | SDS | Note
1 | Complete Final Release Document |  |  |  | #195 | Lê Minh Vương | Done | 1 | 500
2 | Publish project on production |  |  |  | #197 | Lê Minh Vương | Done | 2 | 300
3 | Record video | Edit video User manual |  |  | #201 | Hồ Trọng Nghĩa | Done | 3 | 300
4 | System Test Document | List of all Test Cases implemented in the SaleDock project |  |  | #193 | Đinh Quốc Chương | Done | 1 | 500
5 | Slide for UC-E-1-1, UC-E-1-2, UC-E-1-3 |  |  |  | #200 | Lâm Mỹ Linh | Done | 1 | 200
6 | Slide for UC-E-1-4, UC-E-2-1, UC-E-2-2 |  |  |  | #199 | Nguyễn Thái Sơn | Done | 1 | 200
7 | Slide for UC-E-2-3, UC-E-2-4, UC-E-3-1 |  |  |  | #205 | Nguyễn Thị Thúy | Done | 1 | 200
8 | Slide for UC-E-3-2, UC-E-3-3, UC-E-3-4 |  |  |  | #196 | Đinh Quốc Chương | Done | 3 | 200
9 | Slide for UC-E-4-1, UC-E-4-2, UC-E-4-3 |  |  |  | #202 | Hồ Trọng Nghĩa | Done | 1 | 200
10 | Slide for Document |  |  |  | #195 | Đinh Quốc Chương | Done | 2 | 300